## PROJECT PLAN
Project Plan
S.No. | Feature | Dev time | Expected Delivery
1 | Basic chat with text only sending receiving messages | 8hrs | 2017-08-02
2 | Adding attachments images videos docs to chats | 8hrs | 2017-08-03
3 | Add media- location,contact | 4hrs | 2017-08-04
4 | Chat message long press starmsg,info ,delete,copy,forward,archive,pinned chats | 8hrs | 2017-08-07
5 | Chat message sticky header timestamp | 2hrs | 2017-08-08
6 | Chat message forward to other user | 2hrs | 2017-08-08
7 | Chat message delete specific messages | 1hrs | 2017-08-08
8 | Chat message copy messages | 3hrs | 2017-08-09
9 | Chat message status of message(single ticks,double ticks,blue ticks) | 3hrs | 2017-08-09
10 | Caption msg | 10hrs | 2017-08-11
11 | Reply from notification | 20hrs | 2017-08-16
12 | profile(mute,block,spam) | 2hrs | 2017-08-17
13 | Shared media(classify images,docs,links) | 6hrs | 2017-08-18
14 | Hide contact details of user if mob num not present in contacts list or call logs | 8hrs | 2017-08-21
15 | Button on top bar to video call or voice call
16 | View Contact option in menu
17 | Share profile image with others
18 | Edit contact
19 | Custom contact notifications
20 | Settings Option to view media exchanged with this contact with search | 8hrs | 2017-08-22
21 | Settings Option to view documents exchanged with this contact with search
22 | Settings Option to view shared links with contact with search
23 | Settings Option to search the chat for keywords
24 | Settings Option to mute chat with time duration without notification without sounds
25 | Settings Option to Change wallpaper | 8hrs | 2017-08-23
26 | Settings Option to Block
27 | Settings option to clear chat
28 | Settings option to email chat
29 | Settings option to add chat to shortcut
30 | Settings to share contact
31 | List of ongoing chats sorted from latest active to oldest | 8hrs | 2017-08-24
32 | Search all chats for chat names or any text keyword inside chats
33 | Chats display in list with last sent message and timestamp
34 | Broadcast msgs
35 | Long press to delete ,pinned, archive
36 | Take photo from top left button
37 | Msg sent/read status with chat list homescreen
38 | Account - Privacy Who can see Last seen (Show everybody/contacts/no body) | 16hrs | 2017-08-28
39 | Account - Privacy Who can see Profile Picture (Show everybody/contacts/no body)
40 | Account - Privacy Who can see Status (Show everybody/contacts/no body)
41 | Account - Privacy Blocked Contacts click to see list of blocked contacts
42 | Account - Security - Encryption details will just show user a text message that the chats etc are end to end encrypted
43 | Account - Two step verification-require a pin when registering with whatsapp again
44 | Account - Change Number migrates group info, accoutn info to new number.
45 | Account - Delete my account(delete account on whatssapp, erase messages history, delete whatsapp groups
46 | Chats - Enter is send | 8hrs | 2017-08-29
47 | Chats - App Language
48 | Chats - Font size
49 | Chats - Wallpaper
50 | Chats - Backup to google drive, locally,choose account,backup over wifi/4g,include videos
51 | Chats - Chat History Email chat then select specific chat which u want to email
52 | Chats - Chat History Archive All Chats
53 | Chats - Chat history Clear all Chats
54 | Chats - Chat history Delete All Chats
55 | Notifications - play sounds | 8hrs | 2017-08-30
56 | Notification - choose tone
57 | Notification - vibrate
58 | Notification popup notificaiton
59 | Notification light color
60 | Similar notification options for group chat
61 | Data usage- Media auto download when using mobile/wifi | 8hrs | 2017-08-30
62 | Data usage - Lower data usage when using whatsapp call
63 | Contacts settings invite a friend sends link to download the app using any available messaging option in mobile like messenger skype textmsgs etc | 8hrs | 2017-08-31
64 | Contacts Settings show all contacts enable to show hidden contacts
65 | Profile - Change profile image and Name and status and change mobile number
66 | Help - shows faqs contact us terms and privacy policy and app version
67 | Voice Call logs displayed with type of call video or voice and timestamp + call status(success ,miss, declined) | 4hrs | 2017-09-01
68 | Button to start a new call open contact list from there choose contact to voice or video call
69 | Create a new contact
70 | Search contacts
71 | Invite a contacts
72 | Contacts list
73 | Refresh
74 | Help only text data about
75 | Video calls | 4hrs | 2017-09-01
76 | Name of contact
77 | Hangup call
78 | Speaker call
79 | Go to chats
80 | Mute call
81 | background is other contacts profile image
82 | incoming call option to accept decline or send a msg from predefined msgs or custom msg
83 | when calling my front video camera capture shows | 2hrs | 2017-09-03
84 | after call connect a the full screen video shows other person camera view
85 | small window on bottom shows my camera video view
86 | go to chats
87 | switch camera q
88 | mute call
89 | incoming call option to accept decline or send a msg from predefined msgs or custom msg
90 | UI design implementation | 40hrs | 2017-09-08

## target7sept
S.No. | Feature | Expected Delivery |  | Status
2 | Adding attachments images videos docs to chats | 2017-08-29
3 | Add media- location,contact
12 | profile(mute,block,spam)+profile view | 2017-08-30
13 | Shared media(classify images,docs,links) | 2017-08-31
15 | Button on top bar to video call or voice call | 2017-08-31
16 | View Contact option in menu | 2017-08-31
17 | Share profile image with others | 2017-08-31
18 | Edit contact | 2017-08-31
19 | Custom contact notifications | 2017-09-04
20 | Settings Option to view media exchanged with this contact with search | 2017-09-04
21 | Settings Option to view documents exchanged with this contact with search | 2017-09-04
22 | Settings Option to view shared links with contact with search | 2017-09-04
23 | Settings Option to search the chat for keywordsgp | 2017-09-04
24 | Settings Option to mute chat with time duration without notification without sounds | 2017-09-05
25 | Settings Option to Change wallpaper | 2017-09-05
26 | Settings Option to Block | 2017-09-05
27 | Settings option to clear chat | 2017-09-05
28 | Settings option to email chatgp | 2017-09-05
30 | Settings to share contact | 2017-09-06
31 | List of ongoing chats sorted from latest active to oldestgp | 2017-09-06 | rd
32 | Search all chats for chat names or any text keyword inside chats gp | 2017-09-06
33 | Chats display in list with last sent message and timestamp | 2017-09-07
35 | Long press to delete ,pinned, archive | 2017-09-07 | check whatsapp
36 | Take photo from top left button | 2017-09-07
37 | Msg sent/read status with chat list homescreen gp | 2017-09-07

## Sheet1
Screen | Suggestions
Screen 6 - HomePage | When location Is not enabled | Location Services | Show users nearby | Distance | Age
| 1 . Like Happn show previous matches. | 1.Background enabled .Always like happn | 1. Only online users | 1. Realtime updation (Auto) | 1. Age limit option like tinder
| 2. like Tinder app cannot be accessed. | 2. Location only while using the app - Tinder | 2. Online + offline | 2.Instead of auto update swipe down to referesh
| 3. Don’t show any one nearby.- show a dialog with error |  | 3. Online + offline with status flags | 3. Show distance at the time of screen load only - like tinder
4. Sorting based on distance
screen7 | Like whatsapp (Client)
Screen 8 | 1. Contact that are using the app - whatsapp
2. All contacts like nimbuzz
3. All contacts , ones using the app are shown above
screen 13 | 1.Full screen showing image with name ,distance and age, swipe up reveals common interests
2.Like tinder and happn
screen 9 | 1- Like Ola app
2. Simle puch notification without any tabs , sort by date
screen 10 | Like whatsapp
Screen 11 | Like whatsapp
screen 12 | like whatsapp

## Sheet2
Suggestions Android
Screen | Case | Solution
6-HomePage | Locations not enabled | 1. Happn - Show top overlay asking user to enable location and show last cached users.
2. Tinder - Asks user 10 times to enable location, after that shows profile from last saved location.
3. Woo - Doesn’t even prompt user that his location services are off shows users directly.
| Location services | 1. Happn - No background tracking.
2. Tinder - No background tracking.
3. Woo - No background tracking.
| Show users nearby | 1. Happn- Show users nearby without online/offline status.
2. Tinder - Show users nearby without offline/online status.
3. Woo - Show users nearby without offline/online status.
| Distance | 1. Happn- No distance preference.
2. Tinder - Distance preference can be set. 1mi-100mi
3. Woo - Distance preference can be set. 10-200km
7-Chats |  | Like Whatsapp Client.
8-New Chats |  | 1. Whatsapp-All contacts in mobile contacts.
2. Nimbuzz-Only Contacts using the app .
We can show all contact list of mobile, when user clicks a contact if the contact is using our app the chat will start , if not then he will be taken to invite user interface.
9-Notifications |  | Simple List of notifications pushed by the owner of app to users , no cacheing of notifications for events like new messages etc
10-Attachments drawer |  | Like Whatsapp
11-Chat Page |  | Like Whatsapp
12-Profile Page |  | Like Whatsapp

## Whatsapp
Whatsapp Feature List
Sno | Screen | Feature | Can Toado support | Present in toado | Status | Time
1 | Home Screen-Chats | List of ongoing chats sorted from latest active to oldest | yes | yes |  | 3
|  | Search all chats for chat names or any text keyword inside chats | only search chat names not keywords inside | no | in chat tbd
|  | Chats display in list with last sent message and timestamp | yes | yes
|  | Broadcast msgs | yes | no |  | 2
|  | New Group chat | yes | yes |  | 1
|  | Starred msgs | no | no | tbd | 3
|  | Swipe to change tabs | yes | yes |  | 2
|  | Long press to delete ,pinned, archive | yes | yes |  | 2 | time1 | time2 | total | days | margin
|  | Take photo from top left button | yes | no | tbd | 2 | 81 | 28 | 109 | 13 | 8hrs +/-
|  | Clicking chat list sliding animation opens chat window | yes | no |  | 2
|  | Adding emojis,caption on image, caption with image,crop image,rotate image | no,no,yes,yes,yes,yes | [10 empty] | Features that can be done later | time
|  | Send the photo to any chat in ongoing chats or a new contact | yes | no |  |  | ui | 40 |  |  |  | tbd normal | tbd large(tag messages caption+reply from notif ) | photo can be done later | 20
|  | Frequently conatacted chats and recent chats | no | no |  |  | homescreen | 10 |  |  |  | 14 | 40 | Netowrk usage | 10
|  | Videos from camera option | no | no | no | very long dev time to make custom image/video handler like whatsapp , dev time around 20hrs | total | 159 | [5 empty] | widget | 10
|  | Msg sent/read status with chat list homescreen | yes | no |  | 2
|  | Combine group chats and chats | yes | no |  |  | homescreen+wa without tbd | 169
|  | Button at bottom to start a new chat | yes | yes |  |  |  | 21.125 | add 3 days buffer | 24.125 | 2024-08-01
[7 empty] | homescreen+wa+tbd | 183
2 | Chat screen | Top bar profile image of user can be clicked to view their profile | yes | yes
|  | Shared media with user on profile screen,mute user,block,report spam | yes | yes |  |  |  | 22.875 | add 3 days buffer | 25.875 | 2026-08-01
|  | Custom notifications on profile | no | no | tbd | 2
|  | Encryption | no | no |  | simple text msg would be displayed that the chat is encrypted | homescreen+wa+tbd+tbd large | 223
|  | About user and status displayed on profile image of user | yes | yes |  | 5
|  | Contact details of user mentioned of user | yes | yes |  |  |  | 27.875 | add 5 days buffer | 32.875 | 2004-09-01
|  | Hide contact details of user if mob num not present in contacts list or call logs | yes | no
|  | Button on top bar to video call or voice call | yes | no |  |  |  |  | testing 7 days | 39.875
|  | View Contact option in menu | yes | no
|  | Share profile image with others | yes | no
|  | Edit contact | yes | no
|  | Settings Option to view media exchanged with this contact with search | yes | no |  | 4
|  | Settings Option to view documents exchanged with this contact with search | yes | no
|  | Settings Option to view shared links with contact with search | no | no | tbd 2
|  | Settings Option to search the chat for keywords | yes |  |  | 1
|  | Settings Option to mute chat with time duration without notification without sounds | no | no | tbd | 2
|  | Settings Option to Change wallpaper | yes |  |  | 8
|  | Settings Option to Block | yes
|  | Settings option to clear chat | yes
|  | Settings option to email chat | yes
|  | Settings option to add chat to shortcut | no | no | tbd 5
|  | Settings to share contact | yes
|  | Chat message tag messages with caption | no | no | tbd 10 | will need to custom implement a custom recycler view item view would take long time
|  | Add media- document ,camera,gallery,audio,location,contact | yes,yes,yes,yes,yes,yes | yes |  | 15
|  | Chat message long press starmsg,info ,delete,copy,forward | yes,no,yes,no,yes | no
|  | Chat message sticky header timestamp | yes | yes
|  | Chat message forward to other user | yes
|  | Chat message delete specific messages | no
|  | Chat message copy messages | no
|  | Chat message status of message(single ticks,double ticks,blue ticks) | yes
3 | Settings | Account - Privacy Who can see Last seen (Show everybody/contacts/no body) | yes |  |  | 3
|  | Account - Privacy Who can see Profile Picture (Show everybody/contacts/no body) | yes
|  | Account - Privacy Who can see Status (Show everybody/contacts/no body) | yes
|  | Account - Privacy Blocked Contacts click to see list of blocked contacts | yes
|  | Account - Security - Encryption details will just show user a text message that the chats etc are end to end encrypted | yes
|  | Account - Two step verification-require a pin when registering with whatsapp again | no | no |  | our app flow doesn’t work with this
|  | Account - Change Number migrates group info, accoutn info to new number. | yes |  |  | 2
|  | Account - Delete my account(delete account on whatssapp, erase messages history, delete whatsapp groups | yes
|  | Chats - Enter is send | no | no
|  | Chats - App Language | no | no |  | only in english
|  | Chats - Font size | yes | no |  | 8
|  | Chats - Wallpaper | yes | no
|  | Chats - Backup to google drive, locally,choose account,backup over wifi/4g,include videos | yes,yes,yes,yes,yes,yes | no
|  | Chats - Chat History Email chat then select specific chat which u want to email | yes
|  | Chats - Chat History Archive All Chats | no
|  | Chats - Chat history Clear all Chats | yes
|  | Chats - Chat history Delete All Chats | yes
|  | Notifications - play sounds | yes | no |  | 3
|  | Notification - choose tone | yes | no
|  | Notification - vibrate | yes | no
|  | Notification popup notificaiton | yes | no
|  | Notification light color | no | no
|  | Similar notification options for group chat | yes | no
|  | Network Usage status | no | no | 10 | large overhead to keep track of this and it is doesn’t add any value to the app, user are not tech savy mostly
|  | Data usage- Media auto download when using mobile/wifi | yes | no |  | 3
|  | Data usage - Lower data usage when using whatsapp call | no | no
|  | Contacts settings invite a friend sends link to download the app using any available messaging option in mobile like messenger skype textmsgs etc | yes | yes |  | 1
|  | Contacts Settings show all contacts enable to show hidden contacts | no | no |  | all contacts shown anyways
|  | Profile - Change profile image and Name and status and change mobile number | yes |  |  | 1
|  | Help - shows faqs contact us terms and privacy policy and app version | yes |  |  | 1
4 | Call Screen | Call logs displayed with type of call video or voice and timestamp + call status(success ,miss, declined) | yes | no |  | 1
|  | Button to start a new call open contact list from there choose contact to voice or video call | yes | no
|  | Create a new contact | yes | no |  | 2
|  | Search contacts | yes | no
|  | Invite a contacts | yes | no
|  | Contacts list | yes | no
|  | Refresh | yes | no
|  | Help only text data about | yes | no
| Voice Calling Activity | Type of call video/voice | yes | yes |  | partly done, small additions to be done , 2
|  | Name of contact | yes | yes
|  | Hangup call | yes | yes
|  | Speaker call | yes | yes
|  | Go to chats | yes | yes
|  | Mute call | yes | yes
|  | background is other contacts profile image | yes | yes
|  | incoming call option to accept decline or send a msg from predefined msgs or custom msg | yes | yes
| Video call activity | when calling my front video camera capture shows | yes | yes |  | partly done, small additions to be done , 2
|  | after call connect a the full screen video shows other person camera view | yes | yes
|  | small window on bottom shows my camera video view | yes | yes
|  | go to chats | yes | yes
|  | switch camera q | yes | yes
|  | mute call | yes | yes
|  | incoming call option to accept decline or send a msg from predefined msgs or custom msg | yes | yes
|  | BASIC CHAT+GROUP CHAT SENDING RECEIVEING MSGS THROUGH LOCAL DB |  |  |  | 24
week 1

## revision
S.No. | Feature | Dev time | Expected Delivery | Rev delivery
1 | Basic chat with text only sending receiving messages | 8hrs | 2017-08-02
9 | Chat message status of message(single ticks,double ticks,blue ticks) | 8hrs | 2017-08-07 | 2017-08-16
5 | Chat message sticky header timestamp | 2hrs | 2017-08-08 | 2017-08-16
7 | Chat message delete specific messages | 1hrs | 2017-08-08 | 2017-08-17
8 | Chat message copy messages | 3hrs | 2017-08-09 | 2017-08-17
4 | Chat message long press starmsg,info ,delete,copy,forward chat message | 3hrs | 2017-08-09 | 2017-08-21
10 | Caption msg | 10hrs | 2017-08-11 | 2017-08-22
2 | Adding attachments images videos docs to chats | 8hrs | 2017-08-03 | 2017-08-23
3 | Add media- location,contact | 4hrs | 2017-08-04 | 2017-08-23
12 | profile(mute,block,spam) | 2hrs | 2017-08-17 | 2017-08-24
13 | Shared media(classify images,docs,links) | 6hrs | 2017-08-18 | 2017-08-24
31 | ChatList of ongoing chats sorted from latest active to oldest | 8hrs | 2017-08-24 | 2017-08-25
32 | ChatList Search all chats for chat names or any text keyword inside chats
33 | ChatList Chats display in list with last sent message and timestamp
34 | Broadcast msgs
35 | ChatList Long press to delete ,pinned, archive
36 | Take photo from top left button
37 | ChatList Msg sent/read status with chat list homescreen
20 | Chat window Settings Option to view media exchanged with this contact with search | 8hrs | 2017-08-22 | 2017-08-28
21 | Chat window Settings Option to view documents exchanged with this contact with search
22 | Chat window Settings Option to view shared links with contact with search
23 | Chat window Settings Option to search the chat for keywords
24 | Chat window Settings Option to mute chat with time duration without notification without sounds
25 | Chat window Settings Option to Change wallpaper | 8hrs | 2017-08-23 | 2017-08-29
26 | Chat window Settings Option to Block
27 | Chat window Settings option to clear chat
28 | Chat window Settings option to email chat
29 | Chat window Settings option to add chat to shortcut
30 | Chat window Settings to share contact
38 | Account - Privacy Who can see Last seen (Show everybody/contacts/no body) | 16hrs | 2017-08-28 | 2017-08-31
39 | Account - Privacy Who can see Profile Picture (Show everybody/contacts/no body)
40 | Account - Privacy Who can see Status (Show everybody/contacts/no body)
41 | Account - Privacy Blocked Contacts click to see list of blocked contacts
42 | Account - Security - Encryption details will just show user a text message that the chats etc are end to end encrypted
43 | Account - Two step verification-require a pin when registering with whatsapp again
44 | Account - Change Number migrates group info, accoutn info to new number.
45 | Account - Delete my account(delete account on whatssapp, erase messages history, delete whatsapp groups
46 | Chats - Enter is send | 8hrs | 2017-08-29 | 2017-09-01
47 | Chats - App Language
48 | Chats - Font size
49 | Chats - Wallpaper
50 | Chats - Backup to google drive, locally,choose account,backup over wifi/4g,include videos
51 | Chats - Chat History Email chat then select specific chat which u want to email
52 | Chats - Chat History Archive All Chats
53 | Chats - Chat history Clear all Chats
54 | Chats - Chat history Delete All Chats
55 | Notifications - play sounds | 8hrs | 2017-08-30 | 2017-09-03
56 | Notification - choose tone
57 | Notification - vibrate
58 | Notification popup notificaiton
59 | Notification light color
60 | Similar notification options for group chat
61 | Data usage- Media auto download when using mobile/wifi | 8hrs | 2017-08-30 | 2017-09-04
63 | Contacts settings invite a friend sends link to download the app using any available messaging option in mobile like messenger skype textmsgs etc | 8hrs | 2017-08-31 | 2017-09-05
64 | Contacts Settings show all contacts enable to show hidden contacts
65 | Profile - Change profile image and Name and status and change mobile number
66 | Help - shows faqs contact us terms and privacy policy and app version
67 | Voice Call logs displayed with type of call video or voice and timestamp + call status(success ,miss, declined) | 4hrs | 2017-09-01 | 2017-09-06
68 | Button to start a new call open contact list from there choose contact to voice or video call
69 | Create a new contact
70 | Search contacts
71 | Invite a contacts
72 | Contacts list
73 | Refresh
74 | Help only text data about
75 | Video calls | 4hrs | 2017-09-01 | 2017-09-07
76 | Name of contact
77 | Hangup call
78 | Speaker call
79 | Go to chats
80 | Mute call
81 | background is other contacts profile image
82 | incoming call option to accept decline or send a msg from predefined msgs or custom msg
83 | when calling my front video camera capture shows | 2hrs | 2017-09-03 | 2017-09-08
84 | after call connect a the full screen video shows other person camera view
85 | small window on bottom shows my camera video view
86 | go to chats
87 | switch camera q
88 | mute call
89 | incoming call option to accept decline or send a msg from predefined msgs or custom msg
90 | UI design implementation chats | 8hrs | 2017-09-08 | 2017-09-09
| UI design implementation chatlists | 8hrs |  | 2017-09-11
| UI design implementation tiles screen | 8hrs |  | 2017-09-12
| UI design implementation calls/video | 8hrs |  | 2017-09-13
| UI design implementation of Settings | 8hrs |  | 2017-09-14
11 | Reply from notification | 20hrs | 2017-08-16 | 2017-09-16